WEEKLY STATUS REPORT

Connected Hospitality Limited

| Project Name | BFSCC – Hampton by Hilton Belfast City Centre UnoNet Upgrade |
| --- | --- |
| Customer | Andras House |
| Property / Site | Hampton by Hilton Belfast City Centre |
| Reporting Period | 1st June 2026 – 5th June 2026 |
| Report Number | 1 |
| Project Manager | Mike Best |
| Current Stage | Deployment |
| Status | Issued |

This weekly report provides a concise view of project health, progress, risks, issues, decisions and operational impacts. It is designed for customer review, internal management oversight and stage gate evidence without duplicating the detailed Project Plan, RAID Log or Change Register.

# Document Control

| Field | Detail |
| --- | --- |
| Document Owner | James Harrison |
| Review Frequency | Weekly during active project delivery |
| Status | Controlled project document |
| Related Documents | Project Plan, RAID Log, Change Register, Stage Gate Register, Project Scope Document |

## Version History

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 1.0 |  |  | Initial weekly status report issue |

# 1. Executive Summary

The project continues to progress well, with deployment activities largely on schedule despite several unforeseen infrastructure issues identified during implementation, including cable faults and missing cabling. A project variation has been raised to address the additional scope, and remediation works are already underway. Whilst these findings have resulted in an estimated two-day delay to deployment activities, the team remains focused on completing the majority of installation works by 05/06/2026, with remaining activities continuing on 08/06/2026. Wireless validation and heatmapping are still planned to commence on 09/06/2026 with no current impact to the schedule, and project handover remains targeted to begin from 12/06/2026. Overall, the project remains well managed, with mitigation measures in place and no material risk currently identified to the planned completion and handover dates.

# 2. Project Health Dashboard

| Area | RAG Status | Commentary |
| --- | --- | --- |
| Overall Project | Green | Deployment progressing well |
| Schedule | Amber | In room deployment moving into w/c 8th June due to cable faults |
| Budget | Green | Customer has verbally agreed to costs due to cabling faults |
| Scope | Amber | Unexpected cabling faults have caused variation to scope |
| Risks and Issues | Amber | Further unexpected cabling faults |
| Resources | Green | On site team are equipped to resolve out of scope faults |
| Customer Readiness | Green | Hotel team are supportive of scope changes |
| Operational Impact | Green | None |

RAG ratings should be evidence-based. Green means no intervention is required. Amber means management attention or customer action may be required. Red means tolerance is threatened or breached and escalation is required.

# 3. Progress This Week

| Completed Activity | Outcome / Evidence | Owner |
| --- | --- | --- |
| Firewall Install & Configuration | 1/1 Installed, configured 50% – See Photos/Dashboard | Emannuel Nwokoro/Artur Kellner |
| Core Switch Install & Configuration | 1/1 Installed, configured 75% – See Photos/Dashboard | Emannuel Nwokoro/Artur Kellner |
| Edge Switch Install & Configuration | 5/5 installed, configured 75% – See Photos/Dashboard | Emannuel Nwokoro/Artur Kellner |
| Edge Device Patching | All patched – See Photos | Emannuel Nwokoro/Mike Best |
| ElevenOS Configuration | ElevenOS portal available & tested | Artur Kellner |
| Handoff to admin network | 100% done and tested | Artur Kellner |
| Configuration of SSID’s | 75% done – BFSCC_BOH done, Hilton Honors done and tested, Meeting to be completed | Artur Kellner |
| In Room AP install | 80/101 Completed – See Photos | Mike Best/Tiarnan McKeown |
| Corridor AP Install | 14/16 Completed – See Photos | Mike Best/Tiarnan McKeown |
| Public AP install | 1/4 Completed - See Photos | Mike Best/Tiarnan McKeown |
| Conference AP install | 0/1 Completed - See Photos | Mike Best/Tiarnan McKeown |
| Back Office AP Install | 1/3 Completed - See Photos | Mike Best/Tiarnan McKeown |
| Cable Work Remediation | 14/22 Completed | Mike Best/Tiarnan McKeown |

# 4. Planned Activities Next Week

| Planned Activity | Owner | Target Date | Dependency / Note |
| --- | --- | --- | --- |
| In Room AP Install | Mike Best | 08/06/2026 | Completion of cable fixes |
| Public AP Install | Mike Best | 08/06/2026 | Completion of cable fixes |
| Final switch, wireless & firewall configuration | Artur Kellner | 08/06/2026 | Delayed due to portal access |
| Heatmapping | Ciaran Chambers | 12/06/2026 | Completion of cable fixes & AP installs |
| Site Documentation | Artur Kellner | 12/06/2026 | Completion of cable fixes & AP installs |
| Handover to Support | Artur Kellner | 19/06/2026 | Completion Heatmapping |

# 5. Milestone Status

| Milestone | Baseline Date | Forecast / Actual Date | Status | Commentary |
| --- | --- | --- | --- | --- |
| PID / Scope Approved | 19/05/2026 | 19/05/2026 | Query signature |  |
| Design Approved | 19/05/2026 | 19/05/2026 | Confirmed |  |
| Procurement Complete | 17/05/2026 | 31/05/2026 | Confirmed | Equipment on site |
| Implementation Complete | 12/06/2026 | 12/06/2026 | In progress |  |
| Testing and Commissioning Complete | 12/06/2026 | 12/06/2026 | In progress |  |
| Handover Complete | 19/06/2026 | 19/06/2026 | Pending install |  |

# 6. Risks and Issues Summary

## Top Risks

| ID | Risk Description | Owner | Mitigation / Next Action | Status |
| --- | --- | --- | --- | --- |
| R-001 | Missing cables & cable faults | Mike Best/Richard Banks | Scope variation costs to be agreed | In progress |
| R-002 |  |  |  |  |

## Top Issues

| ID | Issue Description | Owner | Resolution Target | Status |
| --- | --- | --- | --- | --- |
| I-001 | 19 x Cable missing | Mike Best | New cable runs being installed | In progress |
| I-002 | 3 x in room cable faults | Mike Best | Cables being re-terminated | In progress |

# 7. Changes and Variations Summary

| Ref | Change / Variation | Cost Impact | Programme Impact | Status |
| --- | --- | --- | --- | --- |
| CR-001 | Missing cables & Cable faults | TBD | -2 days on deployment | In progress |

# 8. Commercial Summary

| Metric | Value / Status | Commentary |
| --- | --- | --- |
| Contract Value | £7616.12 | 75% paid |
| Approved Variations | TBD |  |
| Pending Variations | None |  |

For customer-facing reports, only include commercial values that have been approved for customer distribution. Internal versions may include forecast margin and cost detail.

# 9. Customer Decisions Required

| Decision / Action Required | Owner | Required By | Impact if Delayed |
| --- | --- | --- | --- |
| Cable faults | Richard Banks | 05/06/2026 | Unable to complete AP installs |

# 10. Resource and Site Access Summary

| Area | Status | Commentary |
| --- | --- | --- |
| Connected Hospitality Resources | Mike Best | Project Lead |
| Connected Hospitality Resources | Emmanuel Nwokoro | Installation of core network |
| Connected Hospitality Resources | Artur Kellner | Remote configuration |
| Connected Hospitality Resources | Ciaran Chambers | Completing heatmapping |
| Subcontractor Resources | Tiarnan McKeown, Donard | Completing installation & cabling |
| Customer Site Access | Hotel operations team | No issues |
| Room / Area Access | Hotel operations team | No issues |
| Permits / RAMS / Inductions | Hotel operations team | No issues |
| Deliveries / Storage | Hotel operations team | All kit present |

# 11. Hospitality Operational Impact

| Operational Area | Impact This Week | Planned Impact Next Week | Controls / Notes |
| --- | --- | --- | --- |
| Guest Rooms | None | Outage for cutover | Planned timing with hotel |
| Public Areas | None | Outage for cutover and downtime during replacement of AP’s | Planned timing with hotel |
| Meeting Rooms / Events | None | Outage for cutover and downtime during replacement of AP’s | Planned timing with hotel |
| Back of House | None | None |  |
| Network / System Outage Windows | None | Cutover will require outage | Timing to be agreed with hotel |
| Guest Experience | None | Loss of service during cutover |  |

# 12. Brand, Compliance and Technical Assurance

| Requirement | Status | Evidence / Commentary |
| --- | --- | --- |
| Hilton Brand Standard | Compliance in progress | Gateway active, coverage TBC |
| Customer Technical Standard | N/A |  |
| Cybersecurity / Data Protection | N/A |  |
| Testing / Commissioning Evidence | Being collected | To be submitted 12/06/26 |
| Handover Evidence | Being collected | To be submitted 19/06/26 |

# 13. Project Manager Commentary

The project has continued to progress positively this reporting period, with deployment activities advancing largely in line with the agreed programme. During implementation, several unforeseen infrastructure issues were identified, including cable faults and missing cabling within existing pathways. In addition, a total of 19 cable locations were discovered to be missing based on supplied documentation.

As a result of these findings, a project variation has been raised to capture the additional scope and associated remediation works. The engineering team has already commenced corrective actions to address these issues, with the impact currently assessed at approximately two working days against the deployment schedule.

The project team remains focused on maximising installation progress, with the objective of completing all unaffected deployment activities by close of business on 05/06/2026. Remediation and remaining installation works will continue on the 08/06/2026 to ensure the project remains on track.

At this stage, the planned wireless validation and heatmapping activities remain scheduled to commence on 09/06/2026, with no anticipated impact to this phase of the programme. Subject to successful completion of testing and validation, project handover activities are expected to commence from 12/06/2026 as planned.

Overall, while the unforeseen site conditions have introduced a minor delay, the project remains well controlled, with mitigation measures in place and no material risk currently identified to the overall completion and handover objectives.

# 14. Approval and Distribution

| Role | Name | Status / Signature | Date |
| --- | --- | --- | --- |
| Project Manager | Mike Best |  | 05/06/2026 |
| Project Sponsor | James Harrison |  | 05/06/2026 |
| Customer Representative | Richard Banks |  | 05/06/2026 |

## Distribution List

| Recipient | Organisation | Purpose |
| --- | --- | --- |
| James Harrison | Connected Hospitality | Project Sponsor |
| Mike Best | Connected Hospitality | Project Lead |
| Artur Kellner | Connected Hospitality | Deployment Manager |
| Emmanuel Nwokoro | Connected Hospitality | Project Engineer |
| Michel Brouns | Reivernet | General Manager EMEA |
| David Pearce | Reivernet | Project Manager |
| Richard Banks | Andras House | IT Manager |
| Stephen Sellers | Hampton by Hilton Belfast | Hotel General Manager |